## Phase I
Category | Requirement | Testing Methods | Status | Issue | Assigned To | Priority
Sign in Button on Welcome page
| R.1.1 | make sure sign in button goes to sign in page | complete
| R.1.2 | make sure transition is >5 seconds to sign in page | complete
Create New Account Button on Welcome page
| R.2.1 | make sure create new account button goes to create new account page | complete
| R.2.2 | make sure transition is >5 seconds to create new account page | complete
Email for Existing Account
| R.3.1 | check emails with > 1 and < 50 characters | complete
| R.3.2 | test with invalid email domains and without .com,.net, etc. | incomplete | can enter email without .com, .net, etc. | Ben
| R.3.3 | try to login in with email that hasn’t been entered into the database | complete
Email for New Account
| R.4.1 | check emails with > 1 and < 50 characters | complete
| R.4.2 | test with invalid email domains and without .com,.net, etc. | incomplete | can enter email without .com, .net, etc. | Ben
| R.4.3 | try to create multiple accounts with the same email | complete
Password
| R.5.1 | check passwords with > 8 and < 25 characters | complete
| R.5.2 | make sure that you can’t use a different password with an existing account | complete
| R.5.3 | check that password is encrypted | complete
First Name Field
| R.6.1 | check >1 and <25 characters and check both symbols and letters work | incomplete | accepts numbers in name, length requirement fulfilled
| R.6.2 | try typing a symbol or number as the first character | incomplete | accepts numbers
Last Name Field
| R.7.1 | check >1 and <25 characters and check both symbols and letters work | incomplete | accepts numbers in name, length requirement fulfilled
| R.7.2 | try typing a symbol or number as the first character | incomplete | accepts numbers
School Name Selection
| R.8.1 | make sure school selection is through drop box and that it is functioning | incomplete | drop box is not working
| R.8.2 | check that only valid partnered schools are listed | incomplete | no schools listed
Fields on Create Account page
| R.9.1 | all create account fields must pass all previous tests | incomplete | see above issues
Error message on Create Account page
| R.10.1 | check that error pops up when one or more fields are not filled | incomplete | doesn’t require last name
| R.10.2 | check if no first name error says first name is required | complete
| R.10.3 | check if invalid/ no email error says what’s your email address? | complete
| R.10.4 | check if invalid password error says password must be at least 8 characters | complete
Tab
| R.11.1 | check it is easy to maneuver with tab button | complete
Cursor
| R.12.1 | check cursor begins in email field of the sign in page | incomplete | must click on box for cursor
| R.12.2 | check cursor begins in first name field of the create account page | incomplete | must click on box for cursor
| R.12.3 | check cursor begins in the current password field of the change password page | incomplete | must click on box for cursor
| R.12.4 | check cursor begins in the email field of the password reset page | incomplete | must click on box for cursor
| R.12.5 | check cursor begins in the new password field of the new password page | can not test
Submit Button on Create Account Page
| R.13.1 | click submit on create account page and make sure it goes to home page | complete
Code Arcade logo Button
| R.14.1 | check if logged in that the code arcade logo button is linked to homepage | complete
| R.14.2 | check if not logged in that the code arcade logo button is linked to welcome page | complete
| R.14.3 | check transition from pressing button to homepage when logged in >5sec | complete
| R.14.4 | check transition from pressing button to welcome page when not logged in >5sec | complete
Re-Enter Password Field on Create Account page
| R.15.1 | check >8 and more than 25< | complete
| R.15.2 | try entering different password from above field and see if it accepts | complete
Error Message for Email
| R.16.1 | check that error message pops up if logging in with invalid email | complete
| R.16.2 | check error says the email is not registered | complete
| R.16.3 | check error message appears below all fields | complete
Error Message for Password
| R.17.1 | check that error message pops up if logging in with invalid password | complete
| R.17.2 | check error says the password is incorrect | complete
| R.17.3 | check error message appears below all fields | complete
Forgot Password Button
| R.18.1 | check there is a forgot password button on sign in page | complete
| R.18.2 | check the forgot password button takes you to forgot password page | complete
Submit button on Sign In page
| R.19.1 | check that submit button on sign in page takes to homepage | complete
| R.19.2 | check this takes less than >5 sec | complete
Leaderboard by School
| R.20.1 | make sure 1st school displayed is accurate with score in database | can not test
| R.20.2 | 2nd | can not test
| R.20.3 | 3rd | can not test
| R.20.4 | 4th | can not test
| R.20.5 | 5th | can not test
Leaderboard by Name
| R.21.1 | make sure 1st name displayed is accurate with score in database | can not test
| R.21.2 | 2nd | can not test
| R.21.3 | 3rd | can not test
| R.21.4 | 4th | can not test
| R.21.5 | 5th | can not test
| R.21.6 | 6th | can not test
| R.21.7 | 7th | can not test
| R.21.8 | 8th | can not test
| R.21.9 | 9th | can not test
| R.21.10 | 10th | can not test
Game Options
| R.22.1 | game options must load the most previously saved version of each game the user has programmed | can not test
| R.22.2 | game options link for each game must link to the game page for each respective game | can not test
| R.22.3 | game options link must link to the game page within 5 seconds once game options link is clicked | can not test
Log Out
| R.23.1 | log out button must link to the welcome page | complete
| R.23.2 | log out button must link to the welcome page >5 sec once log out button is clicked | complete
| R.23.3 | log out button must be included on the homepage and every game page | can not test
Change Password button
| R.24.1 | check there is a change password button on home page and all of the games pages and it is represented by a gear symbol | complete
| R.24.2 | make sure that change password button takes you to correct page | complete
| R.24.3 | check you have to be logged in to have option to change password | complete
| R.24.4 | check it takes >5 sec to load | complete
Change Password page
| R.25.1 | check that you have to know current password | complete
| R.25.2 | make sure new password and confirm password have to be the same | complete
| R.25.3 | make sure error notice pops up if any fields are not completed | incomplete | if you don’t know, page gives no notification that anything is wrong, it just wont do anything if you click save changes
| R.25.4 | make sure error pops up if new and confirm new are not the same | complete
| R.25.5 | make sure that save changes ensures new password is in database | complete
| R.25.6 | check that save changes button takes you to login page | incomplete | it just stays on that page
| R.25.7 | check it takes >5 sec to load | can not test
Start Over button on Game page
| R.26.1 | make sure that start over button removes all previous coding | can not test
Hint button on Game Page
| R.27.1 | check that hint button takes >5 sec to open | can not test
| R.27.2 | check that hint button provides valid help for that level | can not test
| R.27.3 | check that hint button is on every game page | can not test
| R.27.4 | check there is unlimited access to hints | can not test
Instruction pop up page
| R.28.1 | check that game instructions pop up in >5 sec after selecting game | can not test
Close button on Instruction pop up page
| R.29.1 | check that closing instructions returns you to game scene | can not test
| R.29.2 | check this transition is >5 sec | can not test
| R.29.3 | check there is a close button on every instructions page | can not test
Game Page
| R.30.1 | make sure that code modifiers can be dragged to appropriate box | can not test
| R.30.2 | check for error message saying, this is not the appropriate field to drag this box into in >5 sec | can not test
| R.30.3 | make sure game changes in the game are correct based on which code was used | can not test
| R.30.4 | make sure changes implemented take >5 seconds | can not test

## Phase II
Category | Testing Methods | Status | Assigned To | Prioroty
Email on Forgot Password page
test with invalid emails
test with >1 and <50 characters
try email without a valid domain
Submit Button on Forgot Password page
test that submit takes you to verification page
test takes > 5 seconds
Verification Code Field
try verification code with >5 and <7 characters
try using different validation codes from different emails
Submit button on Verification page
make sure submit button takes to verification
takes >5 seconds
New Password Field on Reset Password page
test passwords >3 and <25 characters
make sure it can’t be pre-existing password
make sure it is encrypted
Re-Enter Password Field on Reset Password page
test passwords >3 and <25 characters
test different from field above to ensure that both have to be the same
make sure its encrypted
Submit button on Reset Password page
test submit button takes you to home page
takes >5 seconds
Create Account verification
check names that haven’t been added to the system by partnered schools
try making multiple accounts under the same student name